## Sheet1
No. | Task | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3
|  | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
Edmund Ang
1 | Set up framework and Github | bar: Week 1 Mon
2 | Create base classes for teammate | bar: Week 1 Mon
3 | Create Physics engine | bar: Week 1 Mon
4 | Collision detection & Response | bar: Week 1 Mon to Week 1 Tue
5 | Spacial partitioning | bar: Week 1 Tue
6 | Enemy AI waypoints | bar: Week 1 Tue to Week 1 Wed
7 | Enemy AI Pathfinding | bar: Week 1 Tue to Week 1 Thu
8 | Enemy State machine | bar: Week 1 Thu to Week 1 Fri
9 | Enemy Field of vision | bar: Week 1 Fri
10 | Frustum Culling | bar: Week 1 Fri
11 | In-game time system | bar: Week 2 Mon to Week 2 Tue
12 | Dynamic lighting | bar: Week 2 Tue to Week 2 Wed
13 | Compass system | bar: Week 2 Wed to Week 2 Thu
14 | Enemy AI detection warning | bar: Week 2 Thu to Week 2 Fri
15 | Objective Markers | bar: Week 2 Fri
16 | Create level 2 | bar: Week 3 Mon to Week 3 Tue
17 | Touch up AI | bar: Week 3 Tue
18 | Touch up collision response | bar: Week 3 Tue
19 | Touch up physics engine | bar: Week 3 Tue
20 | Help and guide teammates | bar: Week 2 Mon to Week 3 Wed
21 | Documentation | bar: Week 1 Mon to Week 3 Wed
Glenn |  | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
Gerald |  | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
1 | Models | bar: Mon to Tue
2 | Movements | bar: Wed to Thu
3 | Laser | bar: Fri
4 | Doll | bar: Mon
5 | Control weather | bar: Mon
6 | Weather | bar: Tue to Wed
7 | Dynamic weather | bar: Thu to Fri
8 | Level design and planning | bar: Fri to Tue
9 | Button interaction | bar: Tue
10 | Sound | bar: Wed
11 | Sound class | bar: Wed
12 | AI path fix | bar: Wed
13 | Documentation | bar: Mon to Wed
Troy |  | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
1 | Human Models | bar: Mon
2 | Read From Text File | bar: Tue
3 | Keycard | bar: Tue to Wed
4 | Doors | bar: Thu to Fri
5 | Item Pickup | bar: Mon to Tue
6 | Unlocking Doors | bar: Wed to Thu
7 | Night Vision Goggles | bar: Fri
8 | Animation | bar: Mon
9 | Dialogue | bar: Tue
10 | Level 4 Design | bar: Wed
11 | Documentation | bar: Mon to Wed